## Sheet1 (hidden)
DOOR ACCESS FOR INSTALLATION
BLDG | FLOOR | DOOR # | DOOR | BALANCE
1 | GF | 1 | #11A Receiving Dock | RTE FOR REPLACEMENT OF READER ( Waiting for nexus delivery)
1 | GF | 1 | #12A Pump Room | 2pcs Magnetic Lock 2pcs Door Contact ( For Installation)
1 | GF | 1 | #23A Compensation | 1pc Magnetic Lock 1pc Door Contact ( For Installation )
1 | GF | 1 | #23B HR Manager | 1pc Magnetic Lock 1pc Door Contact ( For Installation )
1 | 3F | 1 | #10A Pantry Elevator | 2pcs EML Lock 2pcsDoor Contact
1 | 3F | 1 | #23B Facility Work Shop | 1pc Relay, 2pc Door contact ( For Purchase Relay
2 | GF | 1 | #26B Receiving Dock | RTE FOR REPLACEMENT OF READER
2 | GF | 1 | #27A Pump Room Door 1 | 1pc Magnetic Lock 1pc Door Contact For Installation
2 | GF | 1 | #27B Pump Room Door 2 | 1pc Magnetic Lock 1pc Door Contact For Installation

## Sheet2 (hidden)
[7 empty] | Proposed Uplink |  |  |  |  | Current Uplink
[8 empty] | AERIAL |  |  |  |  | AERIAL
core1-47 | core1-47 | core1- 48 | core1- 48 | core1-49 | core1-49 | 7 | 8 | 9 | 10 | 11 | 12 | core1-49 | core1-49 | core1-47 | core1-47 | core1-51 | core1-51
13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | core1- 50 | core1- 50 | core1- 52 | core1- 52 | core1- 48 | core1- 48
[8 empty] | BURIAL |  |  |  | core-BURIAL | BURIAL
1 | 2 | 3 | 4 | 5 | 6 | core1- 52 | core1- 52 | core1-51 | core1-51 | core1- 50 | core1- 50 | core1-49
13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | core13-1621
Current Uplink

## BLDG.1
BLDG | FLOOR | DOOR # | DOOR NAME | CORESTATION | Workstation (Server) | CORE STATION | RS485 | DM20 | BioStation3 | READER IN | READER OUT | RTE OUT | REMARKS | DOOR CONTACT | EM LOCK | EBG | KEYSWITCH | BALANCE
1 | GF | 1 | #1A Fire Exit 1 | CS40 1 172.30.16.6 |  | CS40 1 172.30.16.6 | Port 1 | 1 |  | 1 | 1 |  | Active | 1 | 1 | 1 | 1
1 | GF | 1 | #2AGenset Room |  |  |  |  | 1 |  | 1 |  | 1 | Active | 1 | 1 | 1 | 1
1 | GF | 1 | #2B UPS Room | [6 empty] | 1 |  | 1 | Active | 1 | 1 | 1 | 1
1 | GF | 1 | #3A Compliance And Audit |  |  |  |  | 1 |  | 1 |  | 1 | Active | 1 | 1 | 1 | 1
1 | GF | 1 | #3B Quality | [6 empty] | 1 |  | 1 | Active | 1 | 1 | 1 | 1
1 | GF | 1 | #4A SWS Entrance Door |  |  |  |  | 1 |  | 1 | 1 |  | Active | 1 | 1 | 1 | 1
1 | GF | 1 | #5A Management |  |  |  |  | 1 |  | 1 |  | 1 | Active | 1 | 1 | 1 | 1
1 | GF | 1 | #6A SWS Emergency Exits Door |  |  |  |  | 1 |  | 1 | 1 |  | Active | 1 | 1 | 1 | 1
1 | GF | 1 | #7A Fire Exit 2 |  |  |  |  | 1 |  | 1 | 1 |  | Active | 1 | 1 | 1 | 1
1 | GF | 1 | #8ATR1 |  |  |  |  | 1 |  | 1 | 1 |  | Active | 1 | 1 | 1 | 1
1 | GF | 1 | #9A TR2 |  |  |  |  | 1 |  | 1 | 1 |  | Active | 1 | 1 | 1 | 1
1 | GF | 1 | #10A Locker Room |  |  |  |  | 1 |  | 1 |  | 1 | Active | 1 | 1 | 1 | 1
1 | GF | 1 | #10B Storage | [6 empty] | 1 |  | 1 | Active | 1 | 1 | 1 | 1
1 | GF | 1 | #11A Receiving Dock |  |  |  |  | 1 |  | 1 | 1 |  | Active | 1 | 1 | 1 | 1
1 | GF | 1 | #12A Pump Room |  |  |  |  | 1 |  | 1 |  | 1 | Active | 1 | 1 | 1 | 1
1 | GF | 1 | #13A Recruitment |  |  |  |  | 1 |  | 1 |  | 1 | Active | 1 | 1 | 1 | 1
1 | GF | 1 | #13B Hero BU1 | [6 empty] | 1 |  | 1 | Active | 1 | 1 | 1 | 1
1 | GF | 1 | #14A Lobby D2 | CS40 1 172.30.16.6 |  | CS40 1 172.30.16.6 | Host | 1 |  | 1 | 1 |  | Active | 2 | 2 | 1 | 1
1 | GF | 1 | #15A Lobby D1 |  |  |  |  | 1 |  | 1 | 1 |  | Active | 2 | 2 | 1 | 1
1 | GF | 1 | #16A 201 |  |  |  |  | 1 |  | 1 |  | 1 | Active | 1 | 1 | 1 | 1
1 | GF | 1 | #16B NOC | [6 empty] | 1 |  | 1 | Active | 1 | 1 | 1 | 1
1 | GF | 1 | #17A Group Meeting Room |  |  |  |  | 1 |  | 1 |  | 1 | Active | 1 | 1 | 1 | 1
1 | GF | 1 | #17B Recruitment 1 | [6 empty] | 1 |  | 1 | Active | 1 | 1 | 1 | 1
1 | GF | 1 | #18A Test Room |  |  |  |  | 1 |  | 1 |  | 1 | Active | 1 | 1 | 1 | 1
1 | GF | 1 | #18B Recruiters | [6 empty] | 1 |  | 1 | Active | 1 | 1 | 1 | 1
1 | GF | 1 | #19A Versant |  |  |  |  | 1 |  | 1 |  | 1 | Active | 1 | 1 | 1 | 1
1 | GF | 1 | #20A Exec. Office 2 |  |  |  |  | 1 |  | 1 |  | 1 | Active | 1 | 1 | 1 | 1
1 | GF | 1 | #20B Exec. Office 1 | [6 empty] | 1 |  | 2 | Active | 1 | 1 | 1 | 1
1 | GF | 1 | #21A Exec. Secretary |  |  |  |  | 1 |  | 1 |  | 1 | Active | 1 | 1 | 1 | 1
1 | GF | 1 | #21B Exec. Meeting | [6 empty] | 1 |  | 1 | Active | 1 | 1 | 1 | 1
1 | GF | 1 | #22A Fire Exit |  |  |  |  | 1 |  | 1 | 1 |  | Active | 1 | 1 | 1 | 1
1 | GF | 1 | #23A Compensation |  |  |  |  | 1 |  | 1 |  | 1 | Active | 1 | 1 | 1 | 1
1 | GF | 1 | #23B HR Manager | [6 empty] | 1 |  | 1 | Active | 1 | 1 | 1 | 1
1 | GF | 1 | #24A IT Room |  |  |  |  | 1 |  | 1 |  | 1 | Active | 1 | 1 | 1 | 1
1 | GF | 1 | #24B HR and admin | [6 empty] | 1 |  | 1 | Active | 1 | 1 | 1 | 1
1 | GF | 1 | IT Office | BS3 172.30.16.10 |  |  |  |  | 1 |  | 1 |  | Active | 1 | 1 | 1 | 1
1 | GF |  | Near Lobby | BS3 172.30.16.9 |  |  |  |  | 1 |  |  |  | Active
1 | GF |  | Near Lobby | BS3 172.30.16.8 |  |  |  |  | 1 |  |  |  | Active
1 | GF |  | Main Entrance | BS3 172.30.16.29 |  |  |  |  | 1 |  |  |  | Active
BLDG.1 GF |  |  | DOORS |  | WorkStation | CORE STATION |  | DM20 | BioStation3 | READER IN | READER OUT | RTE OUT |  | DOOR CONTACT | EM LOCK | EBG | KEYSWITCH
TOTAL |  |  | 36 |  |  |  |  | 24 | 4 | 35 | 11 | 26 |  | 38 | 38 | 36 | 36
BLDG | FLOOR | DOOR # | DOOR NAME | CORESTATION | Workstation | CORE STATION | RS485 | DM20 | BioStation3 | READER IN | READER OUT | RTE OUT | REMARKS | DOOR CONTACT | EM LOCK | EBG | KEYSWITCH | BALANCE
1 | 2F | 1 | #1A Fire Exit 1 | CS40 1 172.30.16.6 |  | CS40 1 172.30.16.6 | Port2 | 1 |  | 1 | 1 |  | Active | 1 | 1 | 1 | 1
1 | 2F | 1 | #2ATQM |  |  |  |  | 1 |  | 1 |  | 1 | Active | 1 | 1 | 1 | 1
1 | 2F | 1 | #2B Verizon Office | [6 empty] | 1 |  | 1 | Active | 1 | 1 | 1 | 1
1 | 2F | 1 | #3A Quality |  |  |  |  | 1 |  | 1 |  | 1 | Active | 1 | 1 | 1 | 1
1 | 2F | 1 | #3B Management | [6 empty] | 1 |  | 1 | Active | 1 | 1 | 1 | 1
1 | 2F | 1 | #4A Operation Manager |  |  |  |  | 1 |  | 1 |  | 1 | Active | 1 | 1 | 1 | 1
1 | 2F | 1 | #4B Dispute | [6 empty] | 1 |  | 1 | Active | 1 | 1 | 1 | 1
1 | 2F | 1 | #5A SWS Emergency Exit 1 |  |  |  |  | 1 |  | 1 | 1 |  | Active | 1 | 1 | 1 | 1
1 | 2F | 1 | #6A Fire Exit 2 |  |  |  |  | 1 |  | 1 | 1 |  | Active | 1 | 1 | 1 | 1
1 | 2F | 1 | #7A Versant 2 |  |  |  |  | 1 |  | 1 |  | 1 | Active | 1 | 1 | 1 | 1
1 | 2F | 1 | #7B IT Programmer | [6 empty] | 1 |  | 1 | Active | 1 | 1 | 1 | 1
1 | 2F | 1 | #8A Test Room |  |  |  |  | 1 |  | 1 |  | 1 | Active | 1 | 1 | 1 | 1
1 | 2F | 1 | #8B Clinic | [6 empty] | 1 |  | 1 | Active | 1 | 1 | 1 | 1
1 | 2F | 1 | #9A Sleeping 3 |  |  |  |  | 1 |  | 1 |  | 1 | Active | 1 | 1 | 1 | 1
1 | 2F | 1 | #9B IT Director | [6 empty] | 1 |  | 1 | Active | 1 | 1 | 1 | 1
1 | 2F | 1 | #10A Conference |  |  |  |  | 1 |  | 1 |  | 1 | Active | 1 | 1 | 1 | 1
1 | 2F | 1 | #11A Admin |  |  |  |  | 1 |  | 1 |  | 1 | Active | 1 | 1 | 1 | 1
1 | 2F | 1 | #11B Sec Compliance Manager | [6 empty] | 1 |  | 1 | Active | 1 | 1 | 1 | 1
1 | 2F | 1 | #12A Custodian |  |  |  |  | 1 |  | 1 |  | 1 | Active | 1 | 1 | 1 | 1
1 | 2F | 1 | #12B IT | [6 empty] | 1 |  | 1 | Active | 1 | 1 | 1 | 1
1 | 2F | 1 | #13A Facilities |  |  |  |  | 1 |  | 1 |  | 1 | Active | 1 | 1 | 1 | 1
1 | 2F | 1 | #13B Fac. Manager Office | [6 empty] | 1 |  | 3 | Active | 1 | 1 | 1 | 1
1 | 2F | 1 | #14A Emergency Access Door 2 | CS40 1 172.30.16.6 |  | CS40 1 172.30.16.6 | Port3 | 1 |  | 1 | 1 |  | Active | 1 | 1 | 1 | 1
1 | 2F | 1 | #15A TR3 |  |  |  |  | 1 |  | 1 | 1 |  | Active | 1 | 1 | 1 | 1
1 | 2F | 1 | #16A TR4 |  |  |  |  | 1 |  | 1 | 1 |  | Active | 1 | 1 | 1 | 1
1 | 2F | 1 | #17A SWS Entrance Door 2 |  |  |  |  | 1 |  | 1 | 1 |  | Active | 1 | 1 | 1 | 1
1 | 2F | 1 | #18A Monitoring Room |  |  |  |  | 1 |  | 1 | 1 |  | Active | 1 | 1 | 1 | 1
1 | 2F | 1 | #19A SWS Entrance Door 1 |  |  |  |  | 1 |  | 1 | 1 |  | Active | 1 | 1 | 1 | 1
1 | 2F | 1 | #20A Sleeping Room 1 |  |  |  |  | 1 |  | 1 |  | 1 | Active | 1 | 1 | 1 | 1
1 | 2F | 1 | #20B Sleeping Room 2 | [6 empty] | 1 |  | 1 | Active | 1 | 1 | 1 | 1
1 | 2F | 1 | #21A Compliance |  |  |  |  | 1 |  | 1 |  | 1 | Active | 1 | 1 | 1 | 1
1 | 2F | 1 | #21B HR Director Office | [6 empty] | 1 |  | 1 | Active | 1 | 1 | 1 | 1
1 | 2F | 1 | #22A Artificial |  |  |  |  | 1 |  | 1 | 1 |  | Active | 1 | 1 | 1 | 1
1 | 2F | 1 | #23A Locker Room |  |  |  |  | 1 |  | 1 |  | 1 | Active | 1 | 1 | 1 | 1
1 | 2F | 1 | #24A Storage | CS40 2 172.30.16.7 |  | CS40 2 172.30.16.7 | Port3 | 1 |  | 1 |  | 1 | Active | 1 | 1 | 1 | 1
1 | 2F | 1 | #25A TR5 |  |  |  |  | 1 |  | 1 | 1 |  | Active | 1 | 1 | 1 | 1
1 | 2F | 1 | #26A Hero Bu2 |  |  |  |  | 1 |  | 1 |  | 1 | Active | 1 | 1 | 1 | 1
1 | 2F | 1 | IT Lan Room | BS3 172.30.16.13 |  |  |  |  | 1 |  | 1 |  | Active | 1 | 1 | 1 | 1
1 | 2F |  | Near Monitoring | BS3 172.30.16.11 |  |  |  |  | 1 |  |  |  | Active
1 | 2F |  | Near Monitoring | BS3 172.30.16.12 |  |  |  |  | 1 |  |  |  | Active
1 | 2F |  | Inside Lanroom Core station |  |  | 2
1 | 2F |  | Monitoring Room |  | 1
BLDG.1 2F |  |  | DOORS |  | Work Staiton (Server) | CORE STATION |  | DM20 | BioStation3 | READER 0 IN | READER 1 OUT | RTE OUT |  | DOOR CONTACT | EM LOCK | EBG | KEYSWITCH
TOTAL |  |  | 38 |  | 1 | 2 |  | 26 | 3 | 37 | 12 | 28 |  | 38 | 38 | 38 | 38
BLDG | FLOOR | DOOR # | DOOR | CORESTATION |  | CORE STATION | RS485 | DM20 | BioStation3 | READER IN | READER OUT | RTE OUT | REMARKS | DOOR CONTACT | EM LOCK | EBG | KEYSWITCH | BALANCE
1 | 3F | 1 | #1A Fire Exit 1 | CS40 2 172.30.16.7 |  | CS40 2 172.30.16.7 | Port 0 | 1 |  | 1 | 1 |  | Active | 1 | 1 | 1 | 1
1 | 3F | 1 | #2A TR7 Door 1 |  |  |  |  | 1 |  | 1 | 1 |  | Active | 1 | 1 | 1 | 1
1 | 3F | 1 | #3A Quality 1 |  |  |  |  | 1 |  | 1 |  | 1 | Active | 1 | 1 | 1 | 1
1 | 3F | 1 | #3B Management 1 | [6 empty] | 1 |  | 1 | Active | 1 | 1 | 1 | 1
1 | 3F | 1 | #4A SWS Emergency Exit 1 |  |  |  |  | 1 |  | 1 | 1 |  | Active | 2 | 2 | 1 | 1
1 | 3F | 1 | #5A Quality 2 |  |  |  |  | 1 |  | 1 |  | 1 | Active | 1 | 1 | 1 | 1
1 | 3F | 1 | #5B Management 2 | [6 empty] | 1 |  | 1 | Active | 1 | 1 | 1 | 1
1 | 3F | 1 | #6A TR6 Door 1 |  |  |  |  | 1 |  | 1 | 1 |  | Active | 1 | 1 | 1 | 1
1 | 3F | 1 | #7A SWS Emergency Exit 2 |  |  |  |  | 1 |  | 1 | 1 |  | Active | 1 | 1 | 1 | 1
1 | 3F | 1 | #8A fire Exit 2 |  |  |  |  | 1 |  | 1 | 1 |  | Active | 1 | 1 | 1 | 1
1 | 3F | 1 | #9A TR6 Door 2 |  |  |  |  | 1 |  | 1 | 1 |  | Active | 1 | 1 | 1 | 1
1 | 3F | 1 | #10A Pantry Elevator |  |  |  |  | 1 |  | 1 | 1 |  | Active | 2 | 2 | 1 | 1
1 | 3F | 1 | #11A Auditorium Emergency Exit |  |  |  |  | 1 |  | 1 | 1 |  | Active | 1 | 1 | 1 | 1
1 | 3F | 1 | #12A Toiletries Storage |  |  |  |  | 1 |  | 1 |  | 1 | Active | 1 | 1 | 1 | 1
1 | 3F | 1 | #13A Near Stairs Storage |  |  |  |  | 1 |  | 1 |  | 1 | Active | 1 | 1 | 1 | 1
1 | 3F | 1 | #13B Office Supplies Storage | [6 empty] | 1 |  | 1 | Active | 1 | 1 | 1 | 1
1 | 3F | 1 | #14A Auditorium 1 |  |  |  |  | 1 |  | 1 | 1 |  | Active | 1 | 1 | 1 | 1
1 | 3F | 1 | #15A Locker 4 |  |  |  |  | 1 |  | 1 |  | 1 | Active | 1 | 1 | 1 | 1
1 | 3F | 1 | #16A Locker 3 | CS40 2 172.30.16.7 |  | CS40 2 172.30.16.7 | Port 1 | 1 |  | 1 |  | 1 | Active | 1 | 1 | 1 | 1
1 | 3F | 1 | #16B Hero BU3 | [6 empty] | 1 |  | 1 | Active | 1 | 1 | 1 | 1
1 | 3F | 1 | #17A Accounting Payroll 1 |  |  |  |  | 1 |  | 1 |  | 1 | Active | 1 | 1 | 1 | 1
1 | 3F | 1 | #17B Board Room | [6 empty] | 1 |  | 1 | Active | 1 | 1 | 1 | 1
1 | 3F | 1 | #18A Accounting Payroll |  |  |  |  | 1 |  | 1 |  | 1 | Active | 1 | 1 | 1 | 1
1 | 3F | 1 | #19A COO Office |  |  |  |  | 1 |  | 1 |  | 2 | Active | 1 | 1 | 1 | 1
1 | 3F | 1 | #20A Accounting Director |  |  |  |  | 1 |  | 1 |  | 1 | Active | 1 | 1 | 1 | 1
1 | 3F | 1 | #20B Storage 2 | [6 empty] | 1 |  | 1 | Active | 1 | 1 | 1 | 1
1 | 3F | 1 | #21A SWS Entrance Door |  |  |  |  | 1 |  | 1 | 1 |  | Active | 1 | 1 | 1 | 1
1 | 3F | 1 | #22A TR7 Door 2 |  |  |  |  | 1 |  | 1 | 1 |  | Active | 1 | 1 | 1 | 1
1 | 3F | 1 | #23A IT Storage |  |  |  |  | 1 |  | 1 |  | 1 | Active | 1 | 1 | 1 | 1
1 | 3F | 1 | #23B Facility Work Shop | [6 empty] | 1 |  | 1 | Active | 2 | 2 | 1 | 1
1 | 3F | 1 | #24A IT Lan Room |  |  |  |  | 1 |  | 1 |  | 1 | Active | 1 | 1 | 1 | 1
1 | 3F | 1 | #24B IT Workshop | [6 empty] | 1 |  | 1 | Active | 1 | 1 | 1 | 1
1 | 3F | 1 | IT Office | BS3 172.30.16.16 |  |  |  |  | 1 |  | 1 |  | Active | 1 | 1 | 1 | 1
1 | 3F |  | Near SWS Emergency Exit 1 | BS3 172.30.16.14 |  |  |  |  | 1 |  |  |  | Active
1 | 3F |  | Near SWS Emergency Exit 1 | BS3 172.30.16.15 |  |  |  |  | 1 |  |  |  | Active
BLDG.1 3F |  |  | DOORS |  | Work Staion | CORE STATION |  | DM20 | BioStation3 | READER 0 IN | READER 1 OUT | RTE OUT |  | DOOR CONTACT | EM LOCK | EBG | KEYSWITCH
3F TOTAL |  |  | 33 |  | 1 |  |  | 24 | 3 | 32 | 13 | 21 |  | 36 | 36 | 33 | 33
BLDG.1 TOTAL |  |  | 107 |  | 1 | 2 |  | 74 | 10 | 104 | 36 | 75 |  | 112 | 112 | 107 | 107

## BLDG.2
BLDG | FLOOR | DOOR # | DOOR NAME | CORESTATION | Work Station (Server) | CORE STATION | RS485 | DM20 | BioStation3 | READER IN | READER OUT | RTE OUT | DOOR CONTACT | EM LOCK | EBG | KEYSWITCH | REMARKS | BALANCE
2 | GF | 1 | #1A UPS Room | Core Station 3 172.30.16.27 |  | Core Station 3 172.30.16.27 | Port 0 | 1 |  | 1 |  | 1 | 1 | 1 | 1 | 1 | Active
2 | GF | 1 | #1B Genset Room | [6 empty] | 1 |  | 1 | 1 | 1 | 1 | 1 | Active
2 | GF | 1 | #2A Fire Exit 2 |  |  |  |  | 1 |  | 1 | 1 |  | 1 | 1 | 1 | 1 | Active
2 | GF | 1 | #3A Fire Exit 3 |  |  |  |  | 1 |  | 1 | 1 |  | 1 | 1 | 1 | 1 | Active
2 | GF | 1 | #4A Quality 1 |  |  |  |  | 1 |  | 1 |  | 1 | 1 | 1 | 1 | 1 | Active
2 | GF | 1 | #4B Management 1 | [6 empty] | 1 |  | 1 | 1 | 1 | 1 | 1 | Active
2 | GF | 1 | #5A CMS 1 |  |  |  |  | 1 |  | 1 |  | 1 | 1 | 1 | 1 | 1 | Active
2 | GF | 1 | #5B CMS | [6 empty] | 1 |  | 1 | 1 | 1 | 1 | 1 | Active
2 | GF | 1 | #6A Management 2 |  |  |  |  | 1 |  | 1 |  | 1 | 1 | 1 | 1 | 1 | Active
2 | GF | 1 | #6B Quality 2 | [6 empty] | 1 |  | 1 | 1 | 1 | 1 | 1 | Active
2 | GF | 1 | #7A SWS Emergency Exit 1 |  |  |  |  | 1 |  | 1 | 1 |  | 1 | 1 | 1 | 1 | Active
2 | GF | 1 | #8A Conference |  |  |  |  | 1 |  | 1 |  | 1 | 1 | 1 | 1 | 1 | Active
2 | GF | 1 | #9A Auditorium 2 Emergency Exit |  |  |  |  | 1 |  | 1 | 1 |  | 1 | 1 | 1 | 1 | Active
2 | GF | 1 | #10A Compben |  |  |  |  | 1 |  | 1 |  | 1 | 1 | 1 | 1 | 1 | Active
2 | GF | 1 | #10B Hero Bu4 | [6 empty] | 1 |  | 1 | 1 | 1 | 1 | 1 | Active
2 | GF | 1 | #11A Auditorium 1 |  |  |  |  | 1 |  | 1 | 1 |  | 1 | 1 | 1 | 1 | Active
2 | GF | 1 | #12A Nesting Bay 3 |  |  |  |  | 1 |  | 1 |  | 1 | 1 | 1 | 1 | 1 | Active
2 | GF | 1 | #12B Nesting Bay 4 | [6 empty] | 1 |  | 1 | 1 | 1 | 1 | 1 | Active
2 | GF | 1 | #13A Admin Office |  |  |  |  | 1 |  | 1 |  | 1 | 1 | 1 | 1 | 1 | Active
2 | GF | 1 | #13B Operation | [6 empty] | 1 |  | 1 | 1 | 1 | 1 | 1 | Active
2 | GF | 1 | #14A SD |  |  |  |  | 1 |  | 1 |  | 2 | 1 | 1 | 1 | 1 | Active
2 | GF | 1 | #15A EAS Manager Office |  |  |  |  | 1 |  | 1 |  | 1 | 1 | 1 | 1 | 1 | Active
2 | GF | 1 | #15B Meeting Room | [6 empty] | 1 |  | 1 | 1 | 1 | 1 | 1 | Active
2 | GF | 1 | #16A IT Storage |  |  |  |  | 1 |  | 1 |  | 1 | 1 | 1 | 1 | 1 | Active
2 | GF | 1 | #16B EAS Office | [6 empty] | 1 |  | 1 | 1 | 1 | 1 | 1 | Active
2 | GF | 1 | #17A TR1 |  |  |  |  | 1 |  | 1 | 1 |  | 1 | 1 | 1 | 1 | Active
2 | GF | 1 | #18A TR4 |  |  |  |  | 1 |  | 1 | 1 |  | 1 | 1 | 1 | 1 | Active
2 | GF | 1 | #19A Nesting Bay 1 |  |  |  |  | 1 |  | 1 | 1 |  | 1 | 1 | 1 | 1 | Active
2 | GF | 1 | #20A Lan Room |  |  |  |  | 1 |  | 1 |  | 1 | 1 | 1 | 1 | 1 | Active
2 | GF | 1 | #21A Nesting Bay 2 | Core Station 4 172.30.16.18 |  | Core Station 4 172.30.16.18 | Port 0 | 1 |  | 1 | 1 |  | 1 | 1 | 1 | 1 | Active
2 | GF | 1 | #22A TR2 |  |  |  |  | 1 |  | 1 | 1 |  | 1 | 1 | 1 | 1 | Active
2 | GF | 1 | #23A TR3 |  |  |  |  | 1 |  | 1 | 1 |  | 1 | 1 | 1 | 1 | Active
2 | GF | 1 | #24A SWS Entrance Door |  |  |  |  | 1 |  | 1 | 1 |  | 1 | 1 | 1 | 1 | Active
2 | GF | 1 | #25A Locker 6 |  |  |  |  | 1 |  | 1 |  | 1 | 1 | 1 | 1 | 1 | Active
2 | GF | 1 | #25B Storage | [6 empty] | 1 |  | 1 | 1 | 1 | 1 | 1 | Active
2 | GF | 1 | #26A Receiving Dock |  |  |  |  | 1 |  | 1 | 1 |  | 1 | 1 | 1 | 1 | Active
2 | GF | 1 | #27A Pump Room Door 1 |  |  |  |  | 1 |  | 1 |  | 1 | 1 | 1 | 1 | 1 | Active
2 | GF | 1 | #27B Pump Room Door 2 | [6 empty] | 1 |  | 1 | 1 | 1 | 1 | 1 | Active
2 | GF | 1 | #28A Data Center Staging Area |  |  |  |  | 1 |  | 1 | 1 |  | 1 | 1 | 1 | 1 | Active
2 | GF | 1 | #29A Pacu room Staging Area |  |  |  |  | 1 |  | 1 | 1 |  | 1 | 1 | 1 | 1 | Active
2 | GF | 1 | #30A NOC |  |  |  |  | 1 |  | 1 |  | 1 | 1 | 1 | 1 | 1 | Active
2 | GF | 1 | #31A SWS Emergency Exit Door 2 |  |  |  |  | 1 |  | 1 | 1 |  | 1 | 1 | 1 | 1 | Active
2 | GF | 1 | IT Room | BS3 172.30.16.21 |  |  |  |  | 1 |  | 1 |  | 1 | 1 | 1 | 1 | Active
2 | GF |  | Back of Receptionist | BS3 172.30.16.19 |  |  |  |  | 1 | [7 empty] | Active
2 | GF |  | Back of Receptionist | BS3 172.30.16.20 |  |  |  |  | 1 | [7 empty] | Active
2 | GF |  | Main Entrance | BS3 172.30.16.28 |  |  |  |  | 1 | [7 empty] | Active
BLDG.2 GF |  |  | DOORS |  | Work Station (Server) | CORE STATION |  | DM20 | BioStation3 | READER IN | READER OUT | RTE OUT | DOOR CONTACT | EM LOCK | EBG | KEYSWITCH
GF TOTAL |  |  | 43 |  |  |  |  | 31 | 4 | 42 | 17 | 27 | 43 | 43 | 43 | 43
BLDG | FLOOR | DOOR # | DOOR NAME | CORESTATION | Work Station (Server) | CORE STATION | RS485 | DM20 | BioStation3 | READER IN | READER OUT | RTE OUT | DOOR CONTACT | EM LOCK | EBG | KEYSWITCH | REMARKS | BALANCE
2 | 2F | 1 | #1A Fire Exit 1 | Core Station 3 172.30.16.27 |  |  | Port 1 | 1 |  | 1 | 1 |  | 1 | 1 | 1 | 1 | Active
2 | 2F | 1 | #2A Management 1 |  |  |  |  | 1 |  | 1 |  | 1 | 1 | 1 | 1 | 1 | Active
2 | 2F | 1 | #2B Quality 1 | [6 empty] | 1 |  | 1 | 1 | 1 | 1 | 1 | Active
2 | 2F | 1 | #3A Operation Manager |  |  |  |  | 1 |  | 1 |  | 1 | 1 | 1 | 1 | 1 | Active
2 | 2F | 1 | #3B CMS 1 | [6 empty] | 1 |  | 1 | 1 | 1 | 1 | 1 | Active
2 | 2F | 1 | #4A CMS 2 |  |  |  |  | 1 |  | 1 |  | 1 | 1 | 1 | 1 | 1 | Active
2 | 2F | 1 | #4B Quality 2 | [6 empty] | 1 |  | 1 | 1 | 1 | 1 | 1 | Active
2 | 2F | 1 | #5A Management 2 |  |  |  |  | 1 |  | 1 |  | 1 | 1 | 1 | 1 | 1 | Active
2 | 2F | 1 | #6A SWS Emergency Exit 1 |  |  |  |  | 1 |  | 1 | 1 |  | 1 | 1 | 1 | 1 | Active
2 | 2F | 1 | #7A Fire Exit 2 |  |  |  |  | 1 |  | 1 | 1 |  | 1 | 1 | 1 | 1 | Active
2 | 2F | 1 | #8A Conference |  |  |  |  | 1 |  | 1 |  | 1 | 1 | 1 | 1 | 1 | Active
2 | 2F | 1 | #8B Clinic | [6 empty] | 1 |  | 1 | 1 | 1 | 1 | 1 | Active
2 | 2F | 1 | #9A HR Manager |  |  |  |  | 1 |  | 1 |  | 1 | 1 | 1 | 1 | 1 | Active
2 | 2F | 1 | #9B TR Office | [6 empty] | 1 |  | 1 | 1 | 1 | 1 | 1 | Active
2 | 2F | 1 | #10A TR Managers |  |  |  |  | 1 |  | 1 |  | 1 | 1 | 1 | 1 | 1 | Active
2 | 2F | 1 | #10B Hero BU5 | [6 empty] | 1 |  | 1 | 1 | 1 | 1 | 1 | Active
2 | 2F | 1 | #11A Sleeping 2 |  |  |  |  | 1 |  | 1 |  | 1 | 1 | 1 | 1 | 1 | Active
2 | 2F | 1 | #11B Sleeping 1 | [6 empty] | 1 |  | 1 | 1 | 1 | 1 | 1 | Active
2 | 2F | 1 | #12A Locker Room |  |  |  |  | 1 |  | 1 |  | 1 | 1 | 1 | 1 | 1 | Active
2 | 2F | 1 | #13A Artificial |  |  |  |  | 1 |  | 1 | 1 |  | 1 | 1 | 1 | 1 | Active
2 | 2F | 1 | #14A EVT Door 2 |  |  |  |  | 1 |  | 1 |  | 1 | 1 | 1 | 1 | 1 | Active
2 | 2F | 1 | #15A Nesting Bay 3 |  |  |  |  | 1 |  | 1 |  | 1 | 1 | 1 | 1 | 1 | Active
2 | 2F | 1 | #15B Nesting bay 4 | [6 empty] | 1 |  | 1 | 1 | 1 | 1 | 1 | Active
2 | 2F | 1 | #16A TR5 |  |  |  |  | 1 |  | 1 | 1 |  | 1 | 1 | 1 | 1 | Active
2 | 2F | 1 | #17A TR6 |  |  |  |  | 1 |  | 1 | 1 |  | 1 | 1 | 1 | 1 | Active
2 | 2F | 1 | #18A TR9 |  |  |  |  | 1 |  | 1 | 1 |  | 1 | 1 | 1 | 1 | Active
2 | 2F | 1 | #19A Nesting Bay 1 |  |  |  |  | 1 |  | 1 | 1 |  | 1 | 1 | 1 | 1 | Active
2 | 2F | 1 | #20A Lan Room |  |  |  |  | 1 |  | 1 |  | 1 | 1 | 1 | 1 | 1 | Active
2 | 2F | 1 | #21A Auditorium 2 Emergency Exit | Core Station 4 172.30.16.18 |  |  | Port 1 | 1 |  | 1 | 1 |  | 1 | 1 | 1 | 1 | Active
2 | 2F | 1 | #22A Auditorium 1 |  |  |  |  | 1 |  | 1 | 1 |  | 1 | 1 | 1 | 1 | Active
2 | 2F | 1 | #23A EVT Door 1 |  |  |  |  | 1 |  | 1 |  | 1 | 1 | 1 | 1 | 1 | Active
2 | 2F | 1 | #23B EVT Door 3 | [6 empty] | 1 |  | 1 | 1 | 1 | 1 | 1 | Active
2 | 2F | 1 | #24A SWS Entrance Door |  |  |  |  | 1 |  | 1 | 1 |  | 1 | 1 | 1 | 1 | Active
2 | 2F | 1 | #25A TR8 |  |  |  |  | 1 |  | 1 | 1 |  | 1 | 1 | 1 | 1 | Active
2 | 2F | 1 | #26A TR7 |  |  |  |  | 1 |  | 1 | 1 |  | 1 | 1 | 1 | 1 | Active
2 | 2F | 1 | #27A TR10 |  |  |  |  | 1 |  | 1 | 1 |  | 1 | 1 | 1 | 1 | Active
2 | 2F | 1 | #28A Nesting Bay 2 Emergency Exit 2 |  |  |  |  | 1 |  | 1 | 1 |  | 1 | 1 | 1 | 1 | Active
2 | 2F | 1 | #29A SWS Emergency Exit 2 |  |  |  |  | 1 |  | 1 | 1 |  | 1 | 1 | 1 | 1 | Active
2 | 2F | 1 | IT Office | BS3 172.30.16.25 |  |  |  |  | 1 |  | 1 |  | 1 | 1 | 1 | 1 | Active
2 | 2F |  | Near EVT Door 1 | BS3 172.30.16.23 |  |  |  |  | 1 | [7 empty] | Active
2 | 2F |  | Near EVT Door 1 | BS3 172.30.16.24 |  |  |  |  | 1 | [7 empty] | Active
2 | 2F |  | Inside IT Office Core Station |  |  | 2
BLDG.2 2F |  |  | DOORS |  | Work Station (Server) | CORE STATION |  | DM20 | BioStation3 | READER IN | READER OUT | RTE OUT | DOOR CONTACT | EM LOCK | EBG | KEYSWITCH
2F TOTAL |  |  | 39 |  |  | 2 |  | 29 | 3 | 38 | 17 | 22 | 39 | 39 | 39 | 39
BLDG | FLOOR | DOOR # | DOOR NAME | CORESTATION | Work Station (Server) | CORE STATION | RS485 | DM20 | BioStation3 | READER IN | READER OUT | RTE OUT | DOOR CONTACT | EM LOCK | EBG | KEYSWITCH | REMARKS | BALANCE
2 | 4F | 1 | #1A Toiletries Storage Door 1 | Core Station 3 172.30.16.27 |  |  | Port 3 | 1 |  | 1 |  | 1 | 1 | 1 | 1 | 1 | Active
2 | 4F | 1 | #1B Custodian Storage Door 2 | [6 empty] | 1 |  | 1 | 1 | 1 | 1 | 1 | Active
2 | 4F | 1 | #2A HR Storage Door 7 |  |  |  |  | 1 |  | 1 |  | 1 | 1 | 1 | 1 | 1 | Active
2 | 4F | 1 | #2B HR Storage Door 8 | [6 empty] | 1 |  | 1 | 1 | 1 | 1 | 1 | Active
2 | 4F | 1 | #3A Recruitment Storage Door 6 |  |  |  |  | 1 |  | 1 |  | 1 | 1 | 1 | 1 | 1 | Active
2 | 4F | 1 | #3B Payroll Storage Door 5 | [6 empty] | 1 |  | 1 | 1 | 1 | 1 | 1 | Active
2 | 4F | 1 | #4A IT Storage Door 10 |  |  |  |  | 1 |  | 1 |  | 1 | 1 | 1 | 1 | 1 | Active
2 | 4F | 1 | #4B IT Storage Door 9 | [6 empty] | 1 |  | 1 | 1 | 1 | 1 | 1 | Active
2 | 4F | 1 | #5A Custodian Storage Door 4 |  |  |  |  | 1 |  | 1 |  | 1 | 1 | 1 | 1 | 1 | Active
2 | 4F | 1 | #5B Custodian Storage Door 3 | [6 empty] | 1 |  | 1 | 1 | 1 | 1 | 1 | Active
2 | 4F | 1 | #6A Perimeter 1 | Core Station 4 172.30.16.18 |  |  | Port 2 | 1 |  | 1 | 1 |  | 1 | 1 | 1 | 1 | Active
2 | 4F | 1 | #7A Perimeter 2 |  |  |  |  | 1 |  | 1 | 1 |  | 1 | 1 | 1 | 1 | Active
2 | 4F | 1 | #8A Fire Exit |  |  |  |  | 1 |  | 1 | 1 |  | 1 | 1 | 1 | 1 | Active
BLDG.2 4F |  |  | DOORS |  | Work Station (Server) | CORE STATION |  | DM20 | BioStation3 | READER IN | READER OUT | RTE OUT | DOOR CONTACT | EM LOCK | EBG | KEYSWITCH
4F TOTAL |  |  | 13 |  |  |  |  | 8 | 0 | 13 | 3 | 10 | 13 | 13 | 13 | 13
BLDG.2 TOTAL |  |  | 95 |  |  | 2 |  | 68 | 7 | 93 | 37 | 59 | 95 | 95 | 95 | 95

## CS40 1 (hidden)
BLDG | FLOOR | DOOR # | DOOR NAME | CORESTATION | RS485 | DM20 | READER IN | READER OUT | RTE OUT | Remarks
1 | GF | 1 | #1A Fire Exit 1 | CS40 1 172.30.16.6 | Port 1 | 1 | 1 | 1 |  | Active
1 | GF | 1 | #2AGenset Room |  |  | 1 | 1 |  | 1 | Active
1 | GF | 1 | #2B UPS Room |  |  |  | 1 |  | 1 | Active
1 | GF | 1 | #3A Compliance And Audit |  |  | 1 | 1 |  | 1 | Active
1 | GF | 1 | #3B Quality |  |  |  | 1 |  | 1 | Active
1 | GF | 1 | #4A SWS Entrance Door |  |  | 1 | 1 | 1 |  | Active
1 | GF | 1 | #5A Management |  |  | 1 | 1 |  | 1 | Active
1 | GF | 1 | #6A SWS Emergency Exits Door |  |  | 1 | 1 | 1 |  | Active
1 | GF | 1 | #7A Fire Exit 2 |  |  | 1 | 1 | 1 |  | Active
1 | GF | 1 | #8ATR1 |  |  | 1 | 1 | 1 |  | Active
1 | GF | 1 | #9A TR2 |  |  | 1 | 1 | 1 |  | Active
1 | GF | 1 | #10A Locker Room |  |  | 1 | 1 |  | 1 | Active
1 | GF | 1 | #11A Receiving Dock |  |  | 1 | 1 |  | 1 | Active
1 | GF | 1 | #11B Storage |  |  |  | 1 |  | 1 | Active
1 | GF | 1 | #12A Pump Room |  |  | 1 | 1 |  | 1 | Inactive
1 | GF | 1 | #13A Recruitment |  |  | 1 | 1 |  | 1 | Active
1 | GF | 1 | #13B Hero BU1 |  |  |  | 1 |  | 1 | Active
|  |  | DOORS | DM20 | READER IN | READER OUT | RTE OUT
CS40 1 172.30.16.6 | RS485 | Port 1 | 17 | 13 | 17 | 6 | 11
BLDG | FLOOR | DOOR # | DOOR NAME | CORESTATION | RS485 | DM20 | READER IN | READER OUT | RTE OUT | Remarks
1 | GF | 1 | #14A Lobby D2 | CS40 1 172.30.16.6 | Host | 1 | 1 | 1 |  | Active
1 | GF | 1 | #15A Lobby D1 |  |  | 1 | 1 | 1 |  | Active
1 | GF | 1 | #16A 201 |  |  | 1 | 1 |  | 1 | Active
1 | GF | 1 | #16B NOC |  |  |  | 1 |  | 1 | Active
1 | GF | 1 | #17A Group Meeting Room |  |  | 1 | 1 |  | 1 | Active
1 | GF | 1 | #17B Recruitment 1 |  |  |  | 1 |  | 1 | Active
1 | GF | 1 | #18A Test Room |  |  | 1 | 1 |  | 1 | Active
1 | GF | 1 | #18B Recruiters |  |  |  | 1 |  | 1 | Active
1 | GF | 1 | #19A Versant |  |  | 1 | 1 |  | 1 | Active
1 | GF | 1 | #20A Exec. Office 2 |  |  | 1 | 1 |  | 1 | Active
1 | GF | 1 | #20B Exec. Office 1 |  |  |  | 1 |  | 2 | Active
1 | GF | 1 | #21A Exec. Secretary |  |  | 1 | 1 |  | 1 | Active
1 | GF | 1 | #21B Exec. Meeting |  |  |  | 1 |  | 1 | Active
1 | GF | 1 | #22A Fire Exit |  |  | 1 | 1 | 1 |  | Active
1 | GF | 1 | #23A Compensation |  |  | 1 | 1 |  | 1 | Inactive
1 | GF | 1 | #23B HR Manager |  |  |  | 1 |  | 1 | Inactive
1 | GF | 1 | #24A IT Room |  |  | 1 | 1 |  | 1 | Active
1 | GF | 1 | #24B HR and admin |  |  |  | 1 |  | 1 | Active
1 | GF | 1 | IT Office |  |  |  |  | 1
|  |  | DOORS | DM20 | READER IN | READER OUT | RTE OUT
CS40 1 172.30.16.6 | RS485 | Host | 19 | 11 | 18 | 4 | 16
BLDG | FLOOR | DOOR # | DOOR NAME | CORESTATION | RS485 | DM20 | READER IN | READER OUT | RTE OUT | Remarks
1 | 2F | 1 | #1A Fire Exit 1 | CS40 1 172.30.16.6 | Port 2 | 1 | 1 | 1 |  | Active
1 | 2F | 1 | #2ATQM |  |  | 1 | 1 |  | 1 | Active
1 | 2F | 1 | #2B Verizon Office |  |  |  | 1 |  | 1 | Active
1 | 2F | 1 | #3A Quality |  |  | 1 | 1 |  | 1 | Active
1 | 2F | 1 | #3B Management |  |  |  | 1 |  | 1 | Active
1 | 2F | 1 | #4A Operation Manager |  |  | 1 | 1 |  | 1 | Active
1 | 2F | 1 | #4B Dispute |  |  |  | 1 |  | 1 | Active
1 | 2F | 1 | #5A SWS Emergency Exit 1 |  |  | 1 | 1 | 1 |  | Active
1 | 2F | 1 | #6A Fire Exit 2 |  |  | 1 | 1 | 1 |  | Active
1 | 2F | 1 | #7A Versant 2 |  |  | 1 | 1 |  | 1 | Active
1 | 2F | 1 | #7B IT Programmer |  |  |  | 1 |  | 1 | Active
1 | 2F | 1 | #8A Test Room |  |  | 1 | 1 |  | 1 | Active
1 | 2F | 1 | #8B Clinic |  |  |  | 1 |  | 1 | Active
1 | 2F | 1 | #9A Sleeping 3 |  |  | 1 | 1 |  | 1 | Active
1 | 2F | 1 | #9B IT Director |  |  |  | 1 |  | 1 | Active
1 | 2F | 1 | #10A Conference |  |  | 1 | 1 |  | 1 | Active
1 | 2F | 1 | #11A Admin |  |  | 1 | 1 |  | 1 | Active
1 | 2F | 1 | #11B Sec Compliance Manager |  |  |  | 1 |  | 1 | Active
1 | 2F | 1 | #12A Custodian |  |  | 1 | 1 |  | 1 | Active
1 | 2F | 1 | #12B IT |  |  |  | 1 |  | 1 | Active
1 | 2F | 1 | #13A Facilities |  |  | 1 | 1 |  | 1 | Active
1 | 2F | 1 | #13B Fac. Manager Office |  |  |  | 1 |  | 3 | Active
|  |  | DOORS | DM20 | READER IN | READER OUT | RTE OUT
CS40 1 172.30.16.6 | RS485 | Port 2 | 22 | 13 | 22 | 3 | 21
BLDG | FLOOR | DOOR # | DOOR NAME | CORESTATION | RS485 | DM20 | READER IN | READER OUT | RTE OUT | Remarks
1 | 2F | 1 | #14A Emergency Access Door 2 | CS40 1 172.30.16.6 | Port 3 | 1 | 1 | 1 |  | Active
1 | 2F | 1 | #15A TR3 |  |  | 1 | 1 | 1 |  | Active
1 | 2F | 1 | #16A TR4 |  |  | 1 | 1 | 1 |  | Active
1 | 2F | 1 | #17A SWS Entrance Door 2 |  |  | 1 | 1 | 1 |  | Active
1 | 2F | 1 | #18A Monitoring Room |  |  | 1 | 1 | 1 |  | Active
1 | 2F | 1 | #19A SWS Entrance Door 1 |  |  | 1 | 1 | 1 |  | Active
1 | 2F | 1 | #20A Sleeping Room 1 |  |  | 1 | 1 |  | 1 | Active
1 | 2F | 1 | #20B Sleeping Room 2 |  |  |  | 1 |  | 1 | Active
1 | 2F | 1 | #21A Compliance |  |  | 1 | 1 |  | 1 | Active
1 | 2F | 1 | #21B HR Director Office |  |  |  | 1 |  | 1 | Active
1 | 2F | 1 | #22A Artificial |  |  | 1 | 1 | 1 |  | Active
1 | 2F | 1 | #23A Locker Room |  |  | 1 | 1 |  | 1 | Active
1 | 2F | 1 | IT Lan Room |  |  |  |  | 1
|  |  | DOORS | DM20 | READER IN | READER OUT | RTE OUT
CS40 1 172.30.16.6 | RS485 | Port 3 | 13 | 10 | 12 | 8 | 5
CS40 2 172.30.16.7 Overall Total |  |  | 71 | 47 | 69 | 21 | 53

## CS40 2 (hidden)
BLDG | FLOOR | DOOR # | DOOR NAME | CORESTATION | RS485 | DM20 | READER IN | READER OUT | RTE OUT | Remarks
1 | 2F | 1 | #24A Storage | CS40 2 172.30.16.7 | Port3 | 1 | 1 |  | 1 | Active
1 | 2F | 1 | #25A TR5 |  |  | 1 | 1 | 1 |  | Active
1 | 2F | 1 | #26A Hero Bu2 |  |  | 1 | 1 |  | 1 | Active
|  |  | DOORS | DM20 | READER IN | READER OUT | RTE OUT
CS40 2 172.30.16.7 | RS485 | Port 3 | 3 | 3 | 3 | 1 | 2
BLDG | FLOOR | DOOR # | DOOR NAME | CORESTATION | RS485 | DM20 | READER IN | READER OUT | RTE OUT | Remarks
1 | 3F | 1 | #1A Fire Exit 1 | CS40 2 172.30.16.7 | Port 0 | 1 | 1 | 1 |  | Active
1 | 3F | 1 | #2A TR7 Door 1 |  |  | 1 | 1 | 1 |  | Active
1 | 3F | 1 | #3A Quality 1 |  |  | 1 | 1 |  | 1 | Active
1 | 3F | 1 | #3B Management 1 |  |  |  | 1 |  | 1 | Active
1 | 3F | 1 | #4A SWS Emergency Exit 1 |  |  | 1 | 1 | 1 |  | Active
1 | 3F | 1 | #5A Quality 2 |  |  | 1 | 1 |  | 1 | Active
1 | 3F | 1 | #5B Management 2 |  |  |  | 1 |  | 1 | Active
1 | 3F | 1 | #6A TR6 Door 1 |  |  | 1 | 1 | 1 |  | Active
1 | 3F | 1 | #7A SWS Emergency Exit 2 |  |  | 1 | 1 | 1 |  | Active
1 | 3F | 1 | #8A fire Exit 2 |  |  | 1 | 1 | 1 |  | Active
1 | 3F | 1 | #9A TR6 Door 2 |  |  | 1 | 1 | 1 |  | Active
1 | 3F | 1 | #10A Pantry Elevator |  |  | 1 | 1 | 1 |  | Active
1 | 3F | 1 | #11A Auditorium Emergency Exit |  |  | 1 | 1 | 1 |  | Active
1 | 3F | 1 | #12A Toiletries Storage |  |  | 1 | 1 |  | 1 | Active
1 | 3F | 1 | #13A Near Stairs Storage |  |  | 1 | 1 |  | 1 | Active
1 | 3F | 1 | #13B Office Supplies Storage |  |  |  | 1 |  | 1 | Active
1 | 3F | 1 | #14A Auditorium 1 |  |  | 1 | 1 | 1 |  | Active
1 | 3F | 1 | #15A Locker 4 |  |  | 1 | 1 |  | 1 | Active
|  |  | DOORS | DM20 | READER IN | READER OUT | RTE OUT
CS40 2 172.30.16.7 | RS485 | Port 0 | 18 | 15 | 18 | 10 | 8
BLDG | FLOOR | DOOR # | DOOR NAME | CORESTATION | RS485 | DM20 | READER IN | READER OUT | RTE OUT | Remarks
1 | 3F | 1 | #16A Locker 3 | CS40 2 172.30.16.7 | Port 1 | 1 | 1 |  | 1 | Active
1 | 3F | 1 | #16B Hero BU3 |  |  |  | 1 |  | 1 | Active
1 | 3F | 1 | #17A Accounting Payroll 1 |  |  | 1 | 1 |  | 1 | Active
1 | 3F | 1 | #17B Board Room |  |  |  | 1 |  | 1 | Active
1 | 3F | 1 | #18A Accounting Payroll |  |  | 1 | 1 |  | 1 | Active
1 | 3F | 1 | #19A COO Office |  |  | 1 | 1 |  | 2 | Active
1 | 3F | 1 | #20A Accounting Director |  |  | 1 | 1 |  | 1 | Active
1 | 3F | 1 | #20B Storage 2 |  |  |  | 1 |  | 1 | Active
1 | 3F | 1 | #21A SWS Entrance Door |  |  | 1 | 1 | 1 |  | Active
1 | 3F | 1 | #22A TR7 Door 2 |  |  | 1 | 1 | 1 |  | Active
1 | 3F | 1 | #23A IT Storage |  |  | 1 | 1 |  | 1 | Active
1 | 3F | 1 | #23B Facility Work Shop |  |  |  | 1 |  | 1 | Active
1 | 3F | 1 | #24A IT Lan Room |  |  | 1 | 1 |  | 1 | Active
1 | 3F | 1 | #24B IT Workshop |  |  |  | 1 |  | 1 | Active
1 | 3F | 1 | IT Office |  |  |  |  | 1
|  |  | DOORS | DM20 | READER IN | READER OUT | RTE OUT
CS40 2 172.30.16.7 | RS485 | Port 1 | 15 | 9 | 14 | 3 | 13
CS40 2 172.30.16.7 Overall Total |  |  | 36 | 27 | 35 | 14 | 23

## Cs40 3 ( Service Unit ) (hidden)
BLDG | FLOOR | DOOR # | DOOR NAME | CORESTATION | RS485 | DM20 | READER IN | READER OUT | RTE OUT | Remarks
2 | GF | 1 | #1A UPS Room | Core Station 3 172.30.16.27 | Port 0 | 1 | 1 |  | 1 | Active
2 | GF | 1 | #1B Genset Room |  |  |  | 1 |  | 1 | Active
2 | GF | 1 | #2A Fire Exit 2 |  |  | 1 | 1 | 1 |  | Active
2 | GF | 1 | #3A Fire Exit 3 |  |  | 1 | 1 | 1 |  | Active
2 | GF | 1 | #4A Quality 1 |  |  | 1 | 1 |  | 1 | Active
2 | GF | 1 | #4B Management 1 |  |  |  | 1 |  | 1 | Active
2 | GF | 1 | #5A CMS 1 |  |  | 1 | 1 |  | 1 | Active
2 | GF | 1 | #5B CMS |  |  |  | 1 |  | 1 | Active
2 | GF | 1 | #6A Management 2 |  |  | 1 | 1 |  | 1 | Active
2 | GF | 1 | #6B Quality 2 |  |  |  | 1 |  | 1 | Active
2 | GF | 1 | #7A SWS Emergency Exit 1 |  |  | 1 | 1 | 1 |  | Active
2 | GF | 1 | #8A Conference |  |  | 1 | 1 |  | 1 | Active
2 | GF | 1 | #9A Auditorium 2 Emergency Exit |  |  | 1 | 1 | 1 |  | Active
2 | GF | 1 | #10A Compben |  |  | 1 | 1 |  | 1 | Active
2 | GF | 1 | #10B Hero Bu4 |  |  |  | 1 |  | 1 | Active
2 | GF | 1 | #11A Auditorium 1 |  |  | 1 | 1 | 1 |  | Active
2 | GF | 1 | #12A Nesting Bay 3 |  |  | 1 | 1 |  | 1 | Active
2 | GF | 1 | #12B Nesting Bay 4 |  |  |  | 1 |  | 1 | Active
2 | GF | 1 | #13A Admin Office |  |  | 1 | 1 |  | 1 | Active
2 | GF | 1 | #13B Operation |  |  |  | 1 |  | 1 | Active
2 | GF | 1 | #14A SD |  |  | 1 | 1 |  | 2 | Active
2 | GF | 1 | #15A EAS Manager Office |  |  | 1 | 1 |  | 1 | Active
2 | GF | 1 | #15B Meeting Room |  |  |  | 1 |  | 1 | Active | 2 | GF | 1 | IT Room
2 | GF | 1 | #16A IT Storage |  |  | 1 | 1 |  | 1 | Active
2 | GF | 1 | #16B EAS Office |  |  |  | 1 |  | 1 | Active
2 | GF | 1 | #17A TR1 |  |  | 1 | 1 | 1 |  | Active
2 | GF | 1 | #18A TR4 |  |  | 1 | 1 | 1 |  | Active
2 | GF | 1 | #19A Nesting Bay 1 |  |  | 1 | 1 | 1 |  | Active
2 | GF | 1 | #20A Lan Room |  |  | 1 | 1 |  | 1 | Active
2 | GF | 1 | IT Room |  |  |  |  | 1
|  |  | DOORS | DM20 | READER IN | READER OUT | RTE OUT
CS40 3 172.30.16.27 | RS485 | Port 0 | 30 | 20 | 29 | 9 | 22
BLDG | FLOOR | DOOR # | DOOR NAME | CORESTATION | RS485 | DM20 | READER IN | READER OUT | RTE OUT | Remarks
2 | 2F | 1 | #1A Fire Exit 1 | Core Station 3 172.30.16.27 | Port 1 | 1 | 1 | 1 |  | Active
2 | 2F | 1 | #2A Management 1 |  |  | 1 | 1 |  | 1 | Active
2 | 2F | 1 | #2B Quality 1 |  |  |  | 1 |  | 1 | Active
2 | 2F | 1 | #3A Operation Manager |  |  | 1 | 1 |  | 1 | Active
2 | 2F | 1 | #3B CMS 1 |  |  |  | 1 |  | 1 | Active
2 | 2F | 1 | #4A CMS 2 |  |  | 1 | 1 |  | 1 | Active
2 | 2F | 1 | #4B Quality 2 |  |  |  | 1 |  | 1 | Active
2 | 2F | 1 | #5A Management 2 |  |  | 1 | 1 |  | 1 | Active
2 | 2F | 1 | #6A SWS Emergency Exit 1 |  |  | 1 | 1 | 1 |  | Active
2 | 2F | 1 | #7A Fire Exit 2 |  |  | 1 | 1 | 1 |  | Active
2 | 2F | 1 | #8A Conference |  |  | 1 | 1 |  | 1 | Active
2 | 2F | 1 | #8B Clinic |  |  |  | 1 |  | 1 | Active
2 | 2F | 1 | #9A HR Manager |  |  | 1 | 1 |  | 1 | Active
2 | 2F | 1 | #9B TR Office |  |  |  | 1 |  | 1 | Active
2 | 2F | 1 | #10A TR Managers |  |  | 1 | 1 |  | 1 | Active
2 | 2F | 1 | #10B Hero BU5 |  |  |  | 1 |  | 1 | Active
2 | 2F | 1 | #11A Sleeping 2 |  |  | 1 | 1 |  | 1 | Active
2 | 2F | 1 | #11B Sleeping 1 |  |  |  | 1 |  | 1 | Active
2 | 2F | 1 | #12A Locker Room |  |  | 1 | 1 |  | 1 | Active
2 | 2F | 1 | #13A Artificial |  |  | 1 | 1 | 1 |  | Active
2 | 2F | 1 | #14A EVT Door 2 |  |  | 1 | 1 |  | 1 | Active
2 | 2F | 1 | #15A Nesting Bay 3 |  |  | 1 | 1 |  | 1 | Active
2 | 2F | 1 | #15B Nesting bay 4 |  |  |  | 1 |  | 1 | Active
2 | 2F | 1 | #16A TR5 |  |  | 1 | 1 | 1 |  | Active | 2 | 2F | 1 | IT Office
2 | 2F | 1 | #17A TR6 |  |  | 1 | 1 | 1 |  | Active
2 | 2F | 1 | #18A TR9 |  |  | 1 | 1 | 1 |  | Active
2 | 2F | 1 | #19A Nesting Bay 1 |  |  | 1 | 1 | 1 |  | Active
2 | 2F | 1 | #20A Lan Room |  |  | 1 | 1 |  | 1 | Active
2 | 2F | 1 | IT Office |  |  |  |  | 1
|  |  | DOORS | DM20 | READER IN | READER OUT | RTE OUT
CS40 3 172.30.16.27 | RS485 | Port 1 | 29 | 20 | 28 | 9 | 20
BLDG | FLOOR | DOOR # | DOOR NAME | CORESTATION | RS485 | DM20 | READER IN | READER OUT | RTE OUT | Remarks
2 | 4F | 1 | #1A Toiletries Storage Door 1 | Core Station 4 172.30.16.18 | Port 3 | 1 | 1 |  | 1 | Active
2 | 4F | 1 | #1B Custodian Storage Door 2 |  |  |  | 1 |  | 1 | Active
2 | 4F | 1 | #2A HR Storage Door 7 |  |  | 1 | 1 |  | 1 | Active
2 | 4F | 1 | #2B HR Storage Door 8 |  |  |  | 1 |  | 1 | Active
2 | 4F | 1 | #3A Recruitment Storage Door 6 |  |  | 1 | 1 |  | 1 | Active
2 | 4F | 1 | #3B Payroll Storage Door 5 |  |  |  | 1 |  | 1 | Active
2 | 4F | 1 | #4A IT Storage Door 10 |  |  | 1 | 1 |  | 1 | Active
2 | 4F | 1 | #4B IT Storage Door 9 |  |  |  | 1 |  | 1 | Active
2 | 4F | 1 | #5A Custodian Storage Door 4 |  |  | 1 | 1 |  | 1 | Active
2 | 4F | 1 | #5B Custodian Storage Door 3 |  |  |  | 1 |  | 1 | Active
|  |  | DOORS | DM20 | READER IN | READER OUT | RTE OUT
CS40 3 172.30.16.27 | RS485 | Port 2 | 10 | 5 | 10 | 0 | 10
CS40 3 172.30.16.27 Overall Total |  |  | 69 | 45 | 67 | 18 | 52

## CS40 4 (hidden)
BLDG | FLOOR | DOOR # | DOOR NAME | CORESTATION | RS485 | DM20 | READER IN | READER OUT | RTE OUT | Remarks
2 | GF | 1 | #21A Nesting Bay 2 | Core Station 4 172.30.16.18 | Port 0 | 1 | 1 | 1 |  | Active
2 | GF | 1 | #22A TR2 |  |  | 1 | 1 | 1 |  | Active
2 | GF | 1 | #23A TR3 |  |  | 1 | 1 | 1 |  | Active
2 | GF | 1 | #24A SWS Entrance Door |  |  | 1 | 1 | 1 |  | Active
2 | GF | 1 | #25A Locker 6 |  |  | 1 | 1 |  | 1 | Active
2 | GF | 1 | #26A Storage |  |  | 1 | 1 |  | 1 | Active
2 | GF | 1 | #26B Receiving Dock |  |  |  | 1 |  | 1 | Active
2 | GF | 1 | #27A Pump Room Door 1 |  |  | 1 | 1 |  | 1 | Inactive
2 | GF | 1 | #27B Pump Room Door 2 |  |  |  | 1 |  | 1 | Inactive
2 | GF | 1 | #28A Data Center Staging Area |  |  | 1 | 1 | 1 |  | Active
2 | GF | 1 | #29A Pacu room Staging Area |  |  | 1 | 1 | 1 |  | Active
2 | GF | 1 | #30A NOC |  |  | 1 | 1 |  | 1 | Active
2 | GF | 1 | #31A SWS Emergency Exit Door 2 |  |  | 1 | 1 | 1 |  | Active
|  |  | DOORS | DM20 | READER IN | READER OUT | RTE OUT
CS40 4 172.30.16.18 | RS485 | Port 0 | 13 | 11 | 13 | 7 | 6
BLDG | FLOOR | DOOR # | DOOR NAME | CORESTATION | RS485 | DM20 | READER IN | READER OUT | RTE OUT | Remarks
2 | 2F | 1 | #21A Auditorium 2 Emergency Exit | Core Station 4 172.30.16.18 | Port 1 | 1 | 1 | 1 |  | Active
2 | 2F | 1 | #22A Auditorium 1 |  |  | 1 | 1 | 1 |  | Active
2 | 2F | 1 | #23A EVT Door 1 |  |  | 1 | 1 |  | 1 | Active
2 | 2F | 1 | #23B EVT Door 3 |  |  |  | 1 |  | 1 | Active
2 | 2F | 1 | #24A SWS Entrance Door |  |  | 1 | 1 | 1 |  | Active
2 | 2F | 1 | #25A TR8 |  |  | 1 | 1 | 1 |  | Active
2 | 2F | 1 | #26A TR7 |  |  | 1 | 1 | 1 |  | Active
2 | 2F | 1 | #27A TR10 |  |  | 1 | 1 | 1 |  | Active
2 | 2F | 1 | #28A Nesting Bay 2 Emergency Exit 2 |  |  | 1 | 1 | 1 |  | Active
2 | 2F | 1 | #29A SWS Emergency Exit 2 |  |  | 1 | 1 | 1 |  | Active
|  |  | DOORS | DM20 | READER IN | READER OUT | RTE OUT
CS40 4 172.30.16.18 | RS485 | Port 1 | 10 | 9 | 10 | 8 | 2
BLDG | FLOOR | DOOR # | DOOR NAME | CORESTATION | RS485 | DM20 | READER IN | READER OUT | RTE OUT | Remarks
2 | 4F | 1 | #6A Perimeter 1 | Core Station 4 172.30.16.18 | Port 2 | 1 | 1 | 1 |  | Active
2 | 4F | 1 | #7A Perimeter 2 |  |  | 1 | 1 | 1 |  | Inactive
2 | 4F | 1 | #8A Fire Exit |  |  | 1 | 1 | 1 |  | Active
|  |  | DOORS | DM20 | READER IN | READER OUT | RTE OUT
CS40 4 172.30.16.18 | RS485 | Port 2 | 3 | 3 | 3 | 3 | 0
CS40 4 172.30.16.27 Overall Total |  |  | 26 | 23 | 26 | 18 | 8

## OVERALL TOTAL
BLDG. | DOORS | Workstation (Server) | CORE STATION | DM20 | Biostation 3 | READER 0 IN | READER 1 OUT | RTE | DOOR CONTACT | EM LOCK | EBG | KEYSWITCH
BLDG.1 TOTAL | 107 | 1 | 2 | 74 | 10 | 104 | 36 | 75 | 112 | 112 | 107 | 107
BLDG.2 TOTAL | 95 |  | 2 | 68 | 7 | 93 | 37 | 59 | 95 | 95 | 95 | 95
Spare Total |  |  | 1 | 4 | 1 | 9 |  | 15 |  | 4 | 2 | 2
Overall Total | 202 | 1 | 5 | 146 | 18 | 279 |  | 149 | 207 | 211 | 204 | 204